International Union of Geological Sciences

Manual of Standard Methods

for

Establishing the Global Geochemical Reference Network

Chapter 10

Project Management

Alecos Demetriades1,9, Christopher C. Johnson2,9, David B. Smith9, Anna Ladenberger3,9,

Kate V. Knights4,9, Gloria Prieto Rincón5,9, Gloria Namwi Simubali6,9,

Paula Adánez Sanjuan7,9, Christina Stouraiti8,9, Ariadne Argyraki8,9

1 Institute of Geology and Mineral Exploration, Athens, Hellenic Republic

2 GeoElementary, Derby, United Kingdom

3 Geological Survey of Sweden, Uppsala, Sweden

4 Consultant Geochemist, Dublin, Ireland

5 Servicio Geológico Colombiano, Bogotá, Columbia

6 Geological Survey of Namibia, Windhoek, Namibia

7 Instituto Geológico y Minero de España, Madrid, Spain

8 Department of Geology and Geoenvironment, National and Kapodistrian University of Athens, Hellenic Republic

9 IUGS Commission on Global Geochemical Baselines

2022

Published by

The International Union of Geological Sciences

Commission on Global Geochemical Baselines

It is recommended that reference to this part of the Manual should be made in the following way:

Demetriades, A., Johnson, C.C., Smith, D.B., Ladenberger, A., Knights, K.V., Prieto Rincón, G., Simubali, G.N., Adánez Sanjuan, P., Stouraiti, C. & Argyraki, A., 2022. Project Management. Chapter 10 In: Demetriades, A., Johnson, C.C., Smith, D.B., Ladenberger, A., Adánez Sanjuan, P., Argyraki, A., Stouraiti, C., Caritat, P. de, Knights, K.V., Prieto Rincón, G. & Simubali, G.N.  (Editors), International Union of Geological Sciences Manual of Standard Methods for Establishing the Global Geochemical Reference Network. IUGS Commission on Global Geochemical Baselines, Athens, Hellenic Republic, Special Publication, 2, 487−502.

Published by

The International Union of Geological Sciences

Commission on Global Geochemical Baselines

P.O. Box 640 37, Zografou

GR-157 10 Athens

Hellenic Republic

http://www.iugs.org/

http://www.globalgeochemicalbaselines.eu/

National Library of Greece Cataloguing in Publication Data

A catalogue record for this electronic book is available from the

National Library of Greece

ISBN: 978-618-85049-1-2

Contents

10.1. Introduction	491

10.2. Project management structure	491

10.2.1. National Team members	493

10.2.2. Executive Committee	493

10.2.3. Sampling Committee	494

10.2.4. Quality Control Committee	495

10.2.4.1. Development of Reference Materials	495

10.2.4.2. Quality Control	495

10.2.5. Laboratory Committee	496

10.2.5.1. Sample preparation and storage	496

10.2.5.2. Data acquisition	497

10.2.6. Data Management Committee	498

10.2.7. Data Interpretation and Report Writing Committee	499

10.2.8. Public Relations & Marketing Committee	499

10.3. Publications	500

References	500

Blank back page

## 10.1. Introduction

The preceding chapters of this manual describe all the necessary components for the implementation of the Global Geochemical Reference Network project (for details see Chapters 1 and 2). Darnley et al. (1995, p.87) stated that a global project requires a “single permanent agency to accept formal responsibility for securing funds, managing and coordinating these activities according to scientific guidelines determined by an external advisory committee”. However, to successfully implement such a complex multi-national project, a robust project management structure is needed that is independent of the interest of an individual nation or organisation.

In this chapter, we propose a project management structure based on the experience of two multi-national continental-scale geochemical projects, namely the Forum of European Geological Surveys (FOREGS) Geochemical Atlas of Europe, and the Geochemical Mapping of Agricultural and Grazing land Soil (GEMAS), with 26 and 33 participating countries, respectively (Salminen et al., 2005; Reimann et al., 2014). Both projects relied on transparency, openness and trust among the participants. Most importantly, all the participants in these projects worked as a team with the same vision to reach a common goal. The teamwork spirit is what made both projects successful.

It is worth mentioning at this point the dedication to Professor Bjørn Bølviken written on a signed card by the first multinational team working from the 21st of May 1986 to the 1st of July 1993 for the Regional Geochemical Mapping of the then Western Europe: “Bølviken’s Regional Geochemical Mapping of Western Europe towards the Year 2000: A very important project ahead of its time. Conceived by a person with extreme foresight and supported by Europeans with different cultures, proving that European unity could be realised as long as people meet and discuss matters openly and with integrity. Thank you for bringing us together and hope that we meet again to complete the ‘dream’” (Demetriades et al., 2006, p.43). The ‘dream’ was completed thirteen years later with the publication of the two-volume FOREGS Geochemical Atlas of Europe (Salminen et al., 2005; De Vos, Tarvainen et al., 2006).

It is hoped that applied geochemists from all countries will share the common vision to establish the Global Geochemical Reference Network, and are willing to work as a team towards this common goal.

There is no timeframe yet for the Global Geochemical Reference Network project because there are certain steps that should be carried out before it can start:

- The establishment of a Project Management Structure, which is discussed here.

- Availability of necessary funds in a broad sense, i.e., financial, infrastructure, personnel, etc.

- The implementation of the Global project.

## 10.2. Project management structure

An international project of this magnitude and complexity is a challenge for any management scheme. The proposed management structure for the Global Geochemical Reference Network project is displayed in Figure 10.1. Ideally, the whole project should be managed by a high-power and dedicated Executive Committee consisting of one member from each of the nine continental blocks indicated in Figure 10.2. However, the multi-national nature of the project requires the active involvement of applied geochemists from all continental blocks.

The Executive Committee, depending on the needs and for the efficient running of the project, should be free to set up new Committees and to dissolve Committees, which have already served their purpose. Hence, the proposed management structure should be used as a guide by the Steering Committee of the IUGS Commission on Global Geochemical Baselines. According to the IUGS Statutes and Bylaws, the Steering Committee may decide to establish instead a Sub-commission for the execution of the Global Geochemical Reference Network project.

In the following sections, the role and duties of each committee of the proposed management structure are outlined. Few Committees are assigned a dual or triple role, and this is done for better management.

The membership of each committee should be five, and in exceptional cases where the Executive Committee considers it essential, a maximum of seven. The only exceptions to this recommendation are the Executive and Sampling Committees. The Executive Committee is comprised of one member from each of the other committees, for a total of seven members, including the Project Manager. The Sampling Committee consists of members from each continental block, as shown in Figure 10.2, for a total of nine members.

Figure 10.1. Organisation chart of the proposed project management structure for the Global Geochemical Reference Network project. The blue and red connection lines show the relationships between committees. The red line linkages between committees exhibit the stronger relationship as explained in the text. Drawn with Microsoft™ PowerPoint by Alecos Demetriades, Hellenic Institute of Geology and Mineral Exploration (IGME) and IUGS Commission on Global Geochemical Baselines (IUGS-CGGB).

Figure 10.2. Project management continental blocks. Drawn with Golden Software’s MapViewer v8 by Alecos Demetriades (IGME/IUGS-CGGB).

### 10.2.1. National Team members

There are presently 193 countries that are member states of the United Nations; namely 54 countries are in Africa, 33 in Latin America, 2 in North America, 15 in Asia (East & Southeast), 14 in Australasia & Oceania, 44 in Europe, 7 in the Indian subcontinent, 15 in the Middle East, and 9 in Russia & Neighbouring countries. Hence, each country should be represented by at least one member with expertise in applied geochemistry, a good command of the English language, and leadership skills such as communication, problem-solving and decision-making allowing successful project management. Another requirement is to have studied and understood the procedures described in this Manual. The National Team members will be directly in contact with the Executive Committee, and subsequently with the other Committees as the project progresses.

Each country should submit to the Chair of the Executive Committee a signed commitment for its participation in the Global Geochemical Reference Network project. It is expected that each country has priorly secured the necessary funding for its participation in the project, namely the participation of its member or members in workshops and meetings, and for collecting the samples in its territory. The source of funding could either come from the national budget or sponsorships.

The reason for this condition is to show that there is a sound national interest for participation in the project.

Funding for the purchase of the common equipment that will be used in the project, and the costs of preparation of reference materials, sample preparation and analysis will be sought from other sources, e.g., Governments, European Union, Private Companies, UNESCO, geoscientific associations.

### 10.2.2. Executive Committee

The Steering Committee of the International Union of Geological Sciences’ Commission on Global Geochemical Baselines can function as the interim Executive Committee until the Global Geochemical Reference Network project is ready to start. During this interim period, the seven members of the Executive Committee should be selected according to proven good management and communication skills. Typically, it shall consist of a chairperson, a deputy-chairperson, a secretary, a treasurer and three members. The Chairperson of the Executive Committee shall take a lead position of the Project Manager.

The duties of the Executive Committee shall be:

- To formally set up all committees as shown in Figure 10.1.

- To raise needed funds for the efficient running of the project.

- To facilitate decision making and to find viable solutions to any problems arising during project execution. The biggest problem in multinational projects is funding. Hence, the condition that each country should secure the necessary funds for sampling and participation of its representatives in meetings.

- To coordinate efficiently the whole project, which means that one Executive Committee member should serve on at least one Committee, and take direct measures to deal with any failings.

- To organise regular meetings, and the minutes to be circulated to all project members.

- To organise at least one international annual physical meeting, and virtual meetings whenever is deemed necessary.

- To compile an annual report about project progress, and to mention problems encountered and solutions given.

The motto for the Executive Committee that should be passed on to all the other committees shall be the generation of ‘more geochemical data than meeting minutes’.

As indicated in the organisation chart (Fig. 10.1), the Executive Committee reports to the Steering Committee of the Commission on Global Geochemical Baselines, which in turn reports to the IUGS Executive Committee. The IUGS Council is informed about the work performed by the Commission every four years on the occasion of the International Geological Congress.

### 10.2.3. Sampling Committee

Sampling is the most important phase of an applied geochemical mapping project (Demetriades, 2014, 2021; Demetriades et al., 2018). If any mistakes are made during sampling, they are difficult to trace and correct afterwards. This means that all national sampling teams should be well-trained by experienced field applied geochemists, who are well-acquainted with the sampling methods described in Chapter 3 ‘Sampling’.

The duties of each Sampling Committee member shall be:

To organise in collaboration with the Project Manager the purchase of all the sampling equipment that should be purchased centrally and distributed to all participating countries (see Chapter 3).

To send to each country, according to the estimated total number of solid samples that will be collected, sufficient weight of the two standardised blank solid samples for inserting and packing in the field, i.e., 200 grams per 50 routine samples.

To make field training videos.

To organise field-training workshops in their geographical region.

To monitor the quality of sampling by being in the field with different national sampling teams. Here the Sampling Committee cooperates with the Quality Control Committee in the supervision of the sampling teams in each country.

To collect hard copies of field observations sheets, and the corresponding digital records in Microsoft™ Excel and Comma-separated value (CSV) files. Note: The original field observations sheets to be kept in each country.

To check the field observations sheets, and if mistakes are found to contact the national member.

To collect digital maps of the sampling locations of each sampling medium.

To check the sampling locations of all sample types by plotting new maps and comparing them with the submitted digital maps, and if any mistakes are found to contact the national member.

To collect the coded digital version of all photographs taken for each sample type.

To check the codes of all photographs, and if any mistakes are found to contact the national member.

To submit all digital field records, including photographs, to the Quality Control Committee.

### 10.2.4. Quality Control Committee

The Quality Control Committee shall have a quadruple role. Apart from being responsible for the development of secondary reference materials (SRMs), and the validation of the quality of data produced, it should also facilitate the QA/QC during the two most critical stages of the project, which are sampling and sample preparation. Therefore, the Quality Control Committee must have representatives in the Sampling and Laboratory Committees.

#### 10.2.4.1. Development of Reference Materials

In order to carry out efficiently this role, the members of the Quality Control Committee should have expertise in the procedure for standardising secondary reference materials (SRMs; refer to Chapter 5 ‘Development of Reference Materials for External Quality Control’). Five SRMs of 1 tonne each of different chemical composition of each solid sample type (rock, stream sediment, soil, and overbank/floodplain sediment) should be collected, prepared and standardised (see Section §8.5 of Chapter 8). Further, two solid blank reference materials of 1 tonne each should be prepared (refer to Chapter 5 for details).

The duties for the development of Reference Materials shall be:

- To organise the development of SRMs.

- To organise the development of two blank solid reference materials.

- To write a report for each SRM developed (see Kriete, 2012; Reimann and Kriete, 2014).

- To publish the standardisation results of all SRMs developed in the journal of 'Geostandards and Geoanalytical Research'.

Instead of developing project reference materials, it may be possible to purchase commercial reference materials, provided, of course, suitable ones can be found in sufficient quantities for all sample types and at a reasonable price.

#### 10.2.4.2. Quality Control

The members of the Quality Control (QC) Committee should be well-acquainted with the procedures described in Chapter 7 (‘Quality Control Procedures’), and ideally, they should have applied most of them in their projects. Figure 10.1 shows that the QC Committee has a significant role in the project because it receives data and information from two Committees, namely Sampling and Laboratory. When any problems are found, the QC Committee should contact the aforementioned Committees for explanations and clarifications, and may even contact National Team Members if deemed necessary. As displayed in Figure 10.1, there are strong links with the Laboratory and Sampling Committees because any problems with the quality of the analytical data and field records should be cross-checked in order to deliver data of high quality and integrity to the Data Management Committee.

The duties of this Committee, with respect to the quality control of generated results, shall be:

To organise the randomisation of project samples, their renumbering and insertion of quality control samples, according to the scheme proposed in Chapter 4 (‘Sample Preparation and Storage). This procedure must be done very carefully in the sample preparation laboratory. A good record should be kept of the original project sample numbers, and their corresponding new random numbers, because upon receiving the analytical results the original sample numbers must be reassigned.

To conduct all the data checking and computation steps described in Chapter 7.

To ask for the repeat analysis of sample batches in which errors have been found, and in cases where many errors are identified to demand the reanalysis of the whole sample suite.

To write a well-documented quality control report for each analytical data set, and to mention any problems encountered and solutions given (see GEMAS project QC reports by Reimann et al., 2009, 2011, 2012a).

To check all digital field records, including photographs, and after validation to pass them to the Data Management Committee.

### 10.2.5. Laboratory Committee

This Committee is bestowed a three-fold role, i.e.:

- Sample preparation

- Storage of samples, and

- Data acquisition.

#### 10.2.5.1. Sample preparation and storage

Sample preparation is the next important phase of an applied geochemical mapping project (Demetriades, 2014, 2021). Like sampling, if any mistakes are made during sample preparation, they are difficult to trace and correct afterwards. The solid blank samples that are inserted during sampling in the field, and subsequently prepared along with the routine and field duplicate samples, may provide information about contamination of samples during preparation (refer to Chapter 5). At least two solid blank samples should be inserted in each analytical batch of one hundred samples. The sample preparation laboratory should keep a written and digital record of the samples prepared each day, as this is the only way to backtrack contamination problems, if and when they arise.

Consequently, the first expertise of the Laboratory Committee should be in the procedures described in Chapter 4 ‘Sample preparation and storage’. As sample preparation is just as important as sampling, all samples should be prepared in the same laboratory for this is the only way to ensure that the quality of sample preparation remains the same from the first to the last sample. However, an exception from this condition can be made in case each sample type is prepared in a different but dedicated sample preparation facility, for example,

Rock sample preparation

Soil sample preparation (top and bottom soil samples)

Humus sample preparation

Stream sediment sample preparation

Overbank sediment sample preparation (top and bottom overbank sediment samples) and

Floodplain sediment sample preparation (top and bottom floodplain sediment samples).

This is an acceptable sample preparation scheme because all samples of the same type shall be prepared in the same facility. The scheme that is definitely not recommended is the preparation of samples in each country as this will be exceedingly difficult to supervise and control. It is important to remember that the aim of such a multi-national project of this magnitude is the production of a harmonised and homogeneous database for each sample type regardless of country borders. Hence, any possibilities and risks for inhomogeneities in the quality of samples must be eliminated or minimised.

The duties of the Laboratory Committee with respect to Sample Preparation and Storage shall be:

- To organise, in collaboration with the Project Manager, the purchase of suitable vials for the storage of sample aliquots. Each vial for analysis should be able to hold 100 ml of material, and each vial for the archive samples should hold 200 ml (see Fig. 4.2 in Chapter 4). The same type of vial should be used for the project, solid blank and SRM samples.

- To organise, in collaboration with the Project Manager, the purchase of durable labels on which the sample number and bar or quick response (QR) code can be printed.

- To periodically check the quality of sample preparation, and to ensure that the procedures described in Chapter 4 are strictly followed by the sample preparation laboratory or laboratories.

- To receive the digital files (Microsoft™ Excel or CSV) of the daily sample preparation records, which are subsequently passed on to the Quality Control Committee.

- To organise the safe long-term storage, archiving and future access of all project samples.

- To implement, in cooperation with the Quality Control Committee, the randomisation of ten suites of project samples splits of each solid sample type (see Fig. 4.2 in Chapter 4), and the insertion of quality control samples (see Table 4.1 in Chapter 4). According to the recommendations in Chapter 8, the number of different SRMs submitted in an entire analytical batch of samples must be sufficient to produce satisfactory regression analysis plots. For example, if the active project is collecting:

- (a) Thousands of samples, the number of SRMs inserted into a batch of 100 samples should be a minimum of two.

- (b) Hundreds of samples, then the number of SRMs should be increased to four, and

- (c) A small number of samples (<100) then between 1 in 20 samples and 1 in 10 samples should be an SRM.

- To ensure the safe storage of the five 200 ml archive aliquots of each sample type, and any remaining randomised 100 ml analytical aliquots of each solid sample type (see Fig. 4.2 in Chapter 4).

#### 10.2.5.2. Data acquisition

The members of the Laboratory Committee should be experienced geoanalysts but should not be staff members of the laboratories that shall undertake to analyse the samples of the Global Geochemical Reference Network project. They should be familiar with the requirements summarised in Chapter 6 ‘Geoanalytical Methods and Requirements’. The only change in the analytical methods described that can potentially occur over time is in instrumentation.

The duties of the Laboratory Committee, with respect to the analysis of samples, shall be:

To select the best methods for the chemical analysis of stream water and all solid samples (rock, residual soil, and sediments – stream, overbank, floodplain). It is strongly recommended that the selected analytical methods should be able to analyse 15 to 20 gram-aliquots of each solid sample type.

To select the best methods for the determination of any additional parameters (e.g., mineralogy of rock, soil, and sediment samples; bulk density of soil samples, pH of soil and water samples, etc.).

To select the laboratories for the analysis of each sample suite by the same analytical method and instrumentation.

To agree with each laboratory on the number of international primary reference materials (PRMs) that should be inserted in each batch of 100 samples. According to the recommendation in Chapter 8, the analytical contract should have a requirement for the laboratory to routinely determine primary reference materials usually at a rate of four PRMs at the start and end of each analytical batch.

To agree with each laboratory, using wet chemical extraction methods, the number of reagent blank samples that should be inserted in each batch of 100 samples.

To agree with each laboratory the rate of sample reanalysis per batch of 100 samples (normally every 10th or 20th sample should be reanalysed free of charge).

To agree with each laboratory the recording and submission of the daily analytical batch records in a digital format in the order analysed, and with the following information:

- Sample number

- Laboratory number

- Batch number

- Date/time stamp

- −  Analytical result.

To agree with each laboratory not to censor geochemical data below the detection limit of the analytical method used (Note: This is an important requirement in order to estimate the practical detection limit of each analytical method and for each sample type (see Chapter 7 ‘Quality Control Procedures’).

To include in the contract with the laboratory (a) the reanalysis of batches of samples in which errors have been found by the Quality Control Committee, and (b) the reanalysis of the whole sample suite in the case many errors have been identified.

Upon receipt of the analytical results, the Quality Control Committee should check the raw analytical data according to the instructions given in Section §7.3.1 of Chapter 7 in this Manual.

### 10.2.6. Data Management Committee

The members of this Committee should be well-acquainted with data management and map plotting techniques. In Chapter 9 (‘Data Management and Map Production’), the most common data management, statistical and map plotting procedures and techniques are described. However, computer data processing is continuously progressing, and new interpretative techniques are developed. Hence, the best available map plotting techniques should be utilised.

The duties of the Data Management Committee shall be:

To compile a report about the organisation, storage and access of data and information (i.e., field records, problems encountered during analysis). It is recommended to consult data management strategies used successfully by other geological surveys (e.g., Coats and Harris, 1995; Johnson, 2011; USGS, 2016a, b).

To compile and store the raw analytical data, quality control data and field observations in two different file formats Microsoft™ Excel and CSV (comma-separated values) for access by all interested parties through a dedicated website.

To compile and store all digital photographs for access by all interested parties through a dedicated website.

To calculate basic statistical parameters of all data sets and make them available in a table format, e.g., Microsoft™ Excel or Word or pdf.

To plot several types of geochemical distribution maps.

To organise the project website.

To disseminate the data and information related to project goals and applications.

To conduct regular inspection and maintenance of the database and ensure accessibility by all interested parties.

### 10.2.7. Data Interpretation and Report Writing Committee

The members of this Committee should have a satisfactory command of the English language, and good synthesis and comprehension skills of disparate data and information. They should also be good at communication as they are going to be in contact with all participants of the Global Geochemical Reference Network project.

The duties of the Data Interpretation and Report Writing Committee shall be:

To interpret all data generated by the Global Geochemical Reference Network project.

To compile a detailed report for the geoscientific community.

To compile a concise popular-science report for decision-makers and the general public in collaboration with the Public Relations & Marketing Committee.

To write a concise interpretation of the most noteworthy spatial features of each determinand map, which will be uploaded to the website together with the respective map.

To recommend, in collaboration with the Sampling and QC Committees, the monitoring of selected sample sites after a period of twenty years.

### 10.2.8. Public Relations & Marketing Committee

The members of this Committee should have multilingual capabilities because they will handle all outreach activities in public relations and marketing. This is an important committee for the promotion of the Global Geochemical Reference Network project to the geoscience, public, policy and decision-making communities (Liverman et al., 2008; Stewart and Lewis, 2017). Some forward-thinking Geological Surveys have public relations and marketing experts, and their assistance should be sought for developing an effective strategy (e.g., Tellus surveys of the north of Ireland - Glennon et al., 2016; USGS Communications and Publishing; USGS Media Contacts).

The public relations side of this committee is to communicate and promote the Global Geochemical Reference Network project to the widest possible audience. Whereas the role of the marketing side is to develop strategies and tools for promoting the products and services of the Global Geochemical Reference Network project to potential sponsors.

The duties of the Public Relations & Marketing Committee shall be:

To develop the widest possible awareness of the Global Geochemical Reference Network project and its results firstly within the applied geochemistry community and secondly the earth science society as a whole.

To promote the Global Geochemical Reference Network project by using all available communication tools, e.g., social media, radio, television, articles in newsletters, newspapers, periodicals, etc.

To organise an effective promotion campaign for convincing potential sponsors from industry, scientific societies and the public sector to contribute to the execution of various parts of the project.

As there will be a need to promote and market the Global Geochemical Reference Network project in each participating country, a Public Relations and Marketing (PRM) officer should be appointed with whom the Committee should have a close collaboration throughout the project duration. The national PRM officers, apart from a good command of the local language, must be proficient in English.

## 10.3. Publications

All members of the Global Geochemical Reference Network project are encouraged to write articles for publication in peer-reviewed journals. Publications using data covering the whole globe will be the most difficult to handle with respect to authorship. The amicable solution found for the publication of papers on the project ‘Geochemical Mapping of Agricultural and Grazing land Soil (GEMAS)’ may be used in a modified format to be decided upon because of the hundreds of participant names. The published GEMAS project papers use the following format: the names of the leading authors are placed in order of contribution and at the end, the name ‘The GEMAS Project Team’ is added with a superscript, and all participant names are placed in alphabetical order usually at the bottom left-hand corner of the paper’s first page (e.g., Reimann et al., 2012b; Négrel et al., 2021). Hence, by using this format credit is given to all project participants.

## References

Note: All hyperlinks were checked on the 3rd February 2022.

Coats, J.S. and Harris, J.R., 1995. Database design in geochemistry: BGS experience, in Geological Data Management. In: J.R.A. Giles (Editor), Geological Data Management. Geological Society of London Special Publication No. 97, Geological Society of London Press, London, 25–32; https://doi.org/10.1144/GSL.SP.1995.097.01.04.

Darnley, A.G., Björklund, A., Bølviken, B., Gustavsson, N., Koval, P.V., Plant, J.A., Steenfelt, A., Tauchid, M., Xie, X., Garrett, R.G. & Hall, G.E.M., 1995. A Global Geochemical Database for Environmental and Resource Management. Recommendations for International Geochemical Mapping – Final Report of IGCP Project 259. Earth Science Report 19. UNESCO Publishing, Paris, 122 pp.; http://globalgeochemicalbaselines.eu.176-31-41-129.hs-servers.gr/datafiles/file/Blue_Book_GGD_IGCP259.pdf.

Demetriades, A., 2014. Basic considerations: Sampling, the Key for a Successful Applied Geochemical Survey for Mineral Exploration and Environmental Purposes. Chapter 15.1 In: W.F. McDonough (volume Editor), Analytical Geochemistry/Inorganic Instrument Analysis. In: H.D. Holland & K.K. Turekian (Executive Editors), Treatise on Geochemistry. Elsevier, Oxford, vol. 15, 1−31; https://doi.org/10.1016/B978-0-08-095975-7.01401-7.

Demetriades, A., 2021. Geochemical Mapping. In: D. Alderton & S.A. Elias (Editors), Encyclopӕdia of Geology, 2nd edition. Academic Press, United Kingdom, 6, 267−280; https://doi.org/10.1016/B978-0-08-102908-4.00059-X.

Demetriades, A., Pirc, S., De Vos, W., Ottesen, R.T., Reeder, S., O’Connor, P.J., Bidovec, M., De Vivo, B., Tarvainen, T., Batista, M.J., Lax, K., Halamic, J., Pasieczna, A., Slaninka, I., Birke, M., Siewers, U., Breward, N., Lima, A., Duris, M., Locutura, J., Bel-lan, A., Salpeteur, I., Klein, P., Jordan, G., Mazreku, A. & Petersell, V., 2006. Distribution of elements in floodplain sediment. In: W. De Vos, T. Tarvainen (Chief Editors), R. Salminen, S. Reeder, B. De Vivo, A. Demetriades, S. Pirc, M.J. Batista, K. Marsina, R.T. Ottesen, P.J. O’Connor, M. Bidovec, A. Lima, U. Siewers, B. Smith, H. Taylor, R. Shaw, I. Salpeteur, V. Gregorauskiene, J. Halamic, I. Slaninka, K. Lax, P. Gravesen, M. Birke, N. Breward, E.L. Ander, G. Jordan, M. Duris, P. Klein, J. Locutura, A. Bel-lan, A. Pasieczna, J. Lis, A. Mazreku, A. Gilucis, P. Heitzmann, G. Klaver & V. Petersell, Geochemical Atlas of Europe. Part 2 - Interpretation of Geochemical Maps, Additional Tables, Figures, Maps, and Related Publications. Geological Survey of Finland, Espoo, 41−44; http://weppi.gtk.fi/publ/foregsatlas/articles/Floodplain.pdf.

Demetriades, A., Smith, D.B. & Wang, X., 2018. General concepts of geochemical mapping at global, regional, and local scales for mineral exploration and environmental purposes. In: O.A.B. Licht (Guest Editor), Geochemical Mapping. Special Issue, Geochimica Brasiliensis, 32(2), 136−179; https://doi.org/10.21715/GB2358-2812.2018322136.

De Vos, W., Tarvainen, T., Salminen, R., Reeder, S., De Vivo, B., Demetriades, A., Pirc, S., Batista, M.J., Marsina, K., Ottesen, R.T., O’Connor, P.J., Bidovec, M., Lima, A., Siewers, U., Smith, B., Taylor, H., Shaw, R., Salpeteur, I., Gregorauskiene, V., Halamic, J., Slaninka, I., Lax, K., Gravesen, P., Birke, M., Breward, N., Ander, E.L., Jordan, G., Duris, M., Klein, P., Locutura, J., Bel-lan, A., Pasieczna, A., Lis, J., Mazreku, A., Gilucis, A., Heitzmann, P., Klaver, G. & Petersell, V., 2006. Geochemical Atlas of Europe. Part 2 - Interpretation of Geochemical Maps, Additional Tables, Figures, Maps, and Related Publications.  Geological Survey of Finland, Espoo, 692 pp.; http://weppi.gtk.fi/publ/foregsatlas/.

Glennon, M., Cowan, M. & Scanlon, R., 2016. Stakeholder engagement for regional geoscientific surveying: the Tellus Border communications campaign. Chapter 4 In: M.E. Young (Editor), Unearthed: impacts of the Tellus surveys of the north of Ireland. Dublin. Royal Irish Academy, Dublin, 53−63; https://doi.org/10.7486/DRI.w089fr763.

Johnson, C.C., 2011. Understanding the Quality of Chemical Data from the Urban Environment – Part 1: Quality Control Procedures. Chapter 5, In: C.C. Johnson, A. Demetriades, J. Locutura & R.T. Ottesen (Editors), Mapping the Chemical Environment of Urban Areas.  Wiley-Blackwell, John Wiley & Sons Ltd., Chichester, U.K., 61−76; https://doi.org/10.1002/9780470670071.ch5.

Kriete, C., 2012. Results of the GEMAS ring test as supplied to the participating laboratories. Appendix 2 In: C. Reimann, A. Demetriades, M. Birke, O.A. Eggen, P. Filzmoser, C. Kriete & EuroGeoSurveys Geochemistry Expert Group: The EuroGeoSurveys Geochemical Mapping of Agricultural and grazing land Soils project (GEMAS) – Evaluation of quality control results of particle size estimation by MIR prediction, Pb-isotope and MMI® extraction analyses and results of the GEMAS ring test for the standards Ap and Gr. Geological Survey of Norway, Trondheim, NGU report 2012.051, 54−111;   http://www.ngu.no/upload/Publikasjoner/Rapporter/2012/2012_051.pdf.

Liverman, D.G.E., Pereira, C.P.G. & Marker, B. (Editors), 2008. Communicating Environmental Geoscience. Geological Society, London, Special Publications, 305, 214 pp.; https://doi.org/10.1144/SP305.0.

Négrel, P., Ladenberger, A., Reimann, C., Birke, M., Demetriades, A., Sadeghi, M. & The GEMAS Project Team, 2021. GEMAS: Geochemical distribution of Mg in agricultural soil of Europe. Journal of Geochemical Exploration, 221, 106706, 15 pp.; https://doi.org/10.1016/j.gexplo.2020.106706.

Reimann, C. & Kriete, C., 2014. Trueness of GEMAS Analytical Results - The Ring Test.   Chapter 7 In:  C. Reimann, M. Birke, A. Demetriades, P. Filzmoser & P. O’Connor (Editors), Chemistry of Europe’s Agricultural soils – Part A: Methodology and Interpretation of the GEMAS Data Set. Geologisches Jahrbuch (Reihe B102), Schweizerbarth, Hannover, 61−65; http://www.schweizerbart.de/publications/detail/isbn/9783510968466.

Reimann, C., Demetriades, A., Eggen, O.A., Filzmoser, P. & The EuroGeoSurveys Geochemistry Expert Group, 2009. The EuroGeoSurveys geochemical mapping of agricultural and grazing land soils project (GEMAS) – Evaluation of quality control results of aqua regia extraction analysis. Geological Survey of Norway, Trondheim, NGU report 2009.049, 94 pp.; http://www.ngu.no/upload/Publikasjoner/Rapporter/2009/2009_049.pdf.

Reimann, C., Demetriades, A., Eggen, O.A., Filzmoser, P. & the EuroGeoSurveys Geochemistry Expert Group, 2011. The EuroGeoSurveys GEochemical Mapping of Agricultural and grazing land Soils project (GEMAS) - Evaluation of quality control results of total C and S, total organic carbon (TOC), cation exchange capacity (CEC), XRF, pH, and particle size distribution (PSD) analysis. Geological Survey of Norway, Trondheim, NGU report 2011.043, 90 pp.; http://www.ngu.no/upload/Publikasjoner/Rapporter/2011/2011_043.pdf.

Reimann, C., Demetriades, A., Birke, M., Eggen, O. A., Filzmoser, P., Kriete, C. & EuroGeoSurveys Geochemistry Expert Group, 2012a. The EuroGeoSurveys Geochemical Mapping of Agricultural and grazing land Soils project (GEMAS) – Evaluation of quality control results of particle size estimation by MIR prediction, Pb-isotope and MMI® extraction analyses and results of the GEMAS ring test for the standards Ap and Gr. Geological Survey of Norway, Trondheim, NGU report 2012.051, 136 pp.;   http://www.ngu.no/upload/Publikasjoner/Rapporter/2012/2012_051.pdf.

Reimann, C., Flem, B., Fabian, K., Birke, M., Ladenberger, A., Négrel, P., Demetriades, A., Hoogewerff, J. & The GEMAS Project Team, 2012b. Lead and lead isotopes in agricultural soils of Europe - The continental perspective. Applied Geochemistry, 27, 532−542; https://doi.org/10.1016/j.apgeochem.2011.12.012.

Reimann, C., Birke, M., Demetriades, A., Filzmoser, P. & O'Connor, P. (Editors), 2014. Chemistry of Europe's Agricultural Soils – Part A: Methodology and Interpretation of the GEMAS Data Set. Geologisches Jahrbuch (Reihe B 102), Schweizerbarth, Hannover, 528 pp.; http://www.schweizerbart.de/publications/detail/isbn/9783510968466.

Salminen, R., Batista, M.J., Bidovec, M., Demetriades, A., De Vivo, B., De Vos, W., Duris, M., Gilucis, A., Gregorauskiene, V., Halamic, J., Heitzmann, P., Lima, A., Jordan, G., Klaver, G., Klein, P., Lis, J., Locutura, J., Marsina, K., Mazreku, A., O’Connor, P.J., Olsson, S.Å., Ottesen, R.T., Petersell, V., Plant, J.A., Reeder, S., Salpeteur, I., Sandström, H., Siewers, U., Steenfelt, A. & Tarvainen, T., 2005. FOREGS Geochemical Atlas of Europe, Part 1: Background Information, Methodology and Maps. Geological Survey of Finland, Espoo, 526 pp.; http://weppi.gtk.fi/publ/foregsatlas/.

Stewart, I.S. & Lewis, D., 2017. Communicating contested geoscience to the public: Moving from ‘matters of fact’ to ‘matters of concern’. Earth-Science Reviews, 174, 122−123; https://doi.org/10.1016/j.earscirev.2017.09.003.

USGS, 2016a. USGS Data Management Plan Checklist. United States Geological Survey, 2 pp.; https://www.usgs.gov/products/data-and-tools/data-management/data-management-plans.

USGS, 2016b. A Template for Science Center Data Management Strategies (Version 1). United States Geological Survey, 17 pp.; https://www.usgs.gov/products/data-and-tools/data-management/data-management-plans.

Chairperson of the Working Group on ‘Regional Geochemical Mapping’ (1986-1993) of the then Western European Geological Surveys (WEGS: 1971-1993), succeeded by the Forum of European Geological Surveys (FOREGS: 1993-2005), and presently the European Geological Surveys (EGS: 1995-present; it is noted that FOREGS and EGS coexisted for a period of ten years).

Source: https://www.worldometers.info/united-nations/. In the United Nations member list, there are 2 countries that are non-member states, the Holy See and the State of Palestine, thus making a total of 195 countries. Not included in this total count of 195 countries are 39 dependencies or other territories (https://www.worldometers.info/geography/countries-of-the-world/#example).